## ProjectSchedule
MILP vs RL for Hybrid Biomass & PtX Methanol Synthesis Plant
FEV | Project Start: | 2026-03-02 |  | m/d/y
| Today: | 2026-07-08 |  | d/m/y
| Display Week: | 1 |  |  | 2026-03-02 |  |  |  |  | 2026-03-09 |  |  |  |  | 2026-03-16 |  |  |  |  | 2026-03-23 |  |  |  |  | 2026-03-30 |  |  |  |  | 2026-04-06 |  |  |  |  | 2026-04-13 |  |  |  |  | 2026-04-20 |  |  |  |  | 2026-04-27 |  |  |  |  | 2026-05-04 |  |  |  |  | 2026-05-11 |  |  |  |  | 2026-05-18 |  |  |  |  | 2026-05-25 |  |  |  |  | 2026-06-01 |  |  |  |  | 2026-06-08 |  |  |  |  | 2026-06-15 |  |  |  |  | 2026-06-22 |  |  |  |  | 2026-06-29 |  |  |  |  | 2026-07-06 |  |  |  |  | 2026-07-13 |  |  |  |  | 2026-07-20 |  |  |  |  | 2026-07-27 |  |  |  |  | 2026-08-03 |  |  |  |  | 2026-08-10 |  |  |  |  | 2026-08-17 |  |  |  |  | 2026-08-24 |  |  |  |  | 2026-08-31
 | time axis 2026-03-02 to 2026-09-04
TASK | PROGRESS | START | END | DAYS | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F | M | D | M | D | F
Administrative & Kickstart Process
Onboarding Process | 80% | 2026-03-03 | 2026-03-09 | 7
Visa Application | 100% | 2026-03-13 | 2026-03-18 | 6
RWTH Enrollment | 100% | 2026-03-04 | 2026-03-12 | 9
REST Directive Application | 100% | 2026-03-12 | 2026-03-30 | 19
Task Definition | 70% | 2026-03-04 | 2026-03-30 | 27
Writing
Lit. rev. on different methodologies for the same or similar objective | 80% | 2026-03-16 | 2026-03-23 | 8
Identification of the literature gap | 100% | 2026-03-23 | 2026-03-27 | 5
Selection of reference methodology | 70% | 2026-03-27 | 2026-04-03 | 8
Draft 1 Completion of Objective & Literature Review | % | 2026-04-10 | 2026-04-28 | 19
Draft 1 completion of Methodology | 0% | 2026-04-28 | 2026-05-07 | 10
Completion of thesis defense presentation | 0% | 2026-06-01 | 2026-06-24 | 24
Draft 1 completion of Results, Analysis, and Discussion | 0% | 2026-06-14 | 2026-07-14 | 31
Draft 1 completion of Abstract | 0% | 2026-06-14 | 2026-06-16 | 3
Draft 1 completion of Master Thesis | 0% | 2026-07-04 | 2026-08-10 | 38
Completion of master thesis | 0% | 2026-08-10 | 2026-08-25 | 16
MILP Framework
Model introduction | 100% | 2026-03-09 | 2026-03-19 | 11
Simple model construction practice | 100% | 2026-03-12 | 2026-03-26 | 15
Improvement identification opportunity for the model | 100% | 2026-03-26 | 2026-04-10 | 16
Definition of scenario to analyze | 100% | 2026-03-09 | 2026-03-30 | 22
Run model on different scenarios | 100% | 2026-04-14 | 2026-05-14 | 31
Collection and analysis of results | 100% | 2026-05-02 | 2026-06-07 | 37
RL Framework
Model introduction | 20% | 2026-05-01 | 2026-07-01 | 62
Simple model construction practice | 0% | 2026-06-15 | 2026-06-30 | 16
Improvement & validation identification opportunity | 0% | 2026-07-01 | 2026-07-15 | 15
Run model on different scenarios | 0% | 2026-07-15 | 2026-07-29 | 15
Collection and analysis of results | 0% | 2026-07-09 | 2026-08-05 | 28
Comparison
Analysis of MILP vs RL | 0% | 2026-07-29 | 2026-08-19 | 22
Definition of unit of measurement | 100% | 2026-04-25 | 2026-05-10
Sumamary of result of both frameworks |  | 2026-05-10 | 2026-05-30
Sensitivity analysis of the unit of measurement |  | 2026-05-30 | 2026-06-14
Holiday
Robin's off days | 100% | 2026-04-24 | 2026-05-01
Robin's off days Summer | 100% | 2026-08-17 | 2026-08-28
Thesis Defense Week | 100% | 2026-06-24 | 2026-07-04
Note on E6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.